## Website
KYG | S.No. | Deliverables | Type of Deliverable | Timeline | Requirements | Status
| 1 | Main Website go live - All pages mapped with user journey (Wellness tests) | One-Time
| 2 | Blogs | Recurring (5/week)
| 3 | Maintenance of 13+1 domain | Recurring with content posting (5domain/day)
Hard2Soft | S.No. | Deliverables | Type of Deliverable | Timeline | Requirements | Status
| 1 | Edit on new page:
|  | Main product page | One-Time
| 2 | Blogs | Recurring (6/Week)
| 3 | AEO/GEO checks | Recurring
| 4 | FAQ checks and Changes | One time |  | Need content | Done
| 5 | Website Changes (Pricing) ¦ Packaging Change | One time
| 7 | HDFC Payment Integration | One time
Realty Canvas | S.No. | Deliverables | Type of Deliverable | Timeline | Requirements | Status
| 1 | Main Website Audit | Recurring
TalentiFi-X | S.No. | Deliverables | Type of Deliverable | Timeline | Requirements | Status
| 1 | SEO/GEO Checks
| 2 | Blog updates | Recurring | 5/week
| 3 | SEO/AEO Pages | Recurring | 2/week
| 4 | Website edits - add media section, ISO certification | One-Time
| 5 | Chet Website LIVE | One-Time | 2026-06-11 |  | Completed
Digitally Next | S.No. | Deliverables | Type of Deliverable | Timeline | Requirements | Status
| 1 | SEO/GEO Checks | Recurring
| 2 | Blog updates | Recurring | 5/week
| 3 | SEO/AEO Pages | Recurring
| 4 | Main Website case study pages | One-Time
Rudione | S.No. | Deliverables | Type of Deliverable | Timeline | Requirements | Status
| 1 | Website Development (Rudione) | One time |  | All pages to be mapped with new packaging design and layout
| 2 | Website Development (Leocym) | One time
| 3 | Payment Gateway Intigation (Testing) | One time
| 4 | Shipping Intigation | One time
| 5 | Sitemap | One time |  | Done (Leocym Sitemap today)
Happy Ganga | S.No. | Deliverables | Type of Deliverable | Timeline | Requirements | Status
| 1 | Website Development | One time | 4th Sept, 2026 | About us, contact us, Category page, Legal page |  | homepage(6th August, 2026), 7th August, 2026
| 3 | Payment Gateway Intigation (Testing) | One time |  |  | Done
| 4 | Shipping Intigation | One time | 2rd sept, 2026
| 5 | Sitemap | One time |  |  | Done

## Graphics
KYG | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | B2B Brochure | One time | A4 | 1 | 8th Sept, 2026
| 2 | D2C Brochure | One time | A4 | 1 | 8th Sept, 2026
| 3 | Test Cards & Infographics: With and without Pricing | One time | Carousel | Acc to tests
|  | Segment-wise package cards |  | Cards
Offer cards
Combo/family package cards
| 4 | How Genetic Testing Works? | One time |  | 2
Explainer infographic
Website section visual
| 5 | Standees (Walk-in, Event centric) | Recurring |  | Event based
| 6 | Certificate template | One time |  | 2026-01-02 |  |  | Done
| 7 | Stamp Design | One time |  | 1 |  |  | Done
| 8 | Report template | One time |  | 2 |  |  | Done
| 9 | Review template | One time |  | 2026-04-05 |  |  | Done
| 10 | Coupon/offers templates | One time |  | 2026-05-06 |  |  | Done
| 14 | Social media | Recurring | Carousels¦ Static¦ Infographics¦ Comic strips¦Conversationals¦ Mindmaps¦ Stories | 2026-05-06 |  |  | In progress
| 15 | Images for 13 additional domains | Recurring |  | 13-15
| 16 | Blog Images | Recurring |  | 2026-08-10 |  |  | In progress
| 17 | UI/UX of main website (9 pages) | One time |  |  | 10th August, 2026 |  | In progress | Test pages (Skin, Kidney, Eye) and remaining pages from last week
| 18 | Comic Strips |  |  | 2026-05-06 | 8th Sept, 2026 |  | In progress
| 19 | Packaging | One time |  |  |  |  | Done
Hard2Soft | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Social Media Assets + festival creatives and website banner | Recurring | Statics ¦ Carousels ¦ Infographics ¦ Comics ¦ Conversational ¦ Thumbnails | 7/week |  |  | In progress
| 2 | Paid Ads assets | Recurring | Change in MRP¦ Design (Subject to feedback) ¦ Acid cleaning and new theme assets | 5*4 assets with sizes | 8th Sept, 2026
| 3 | Blog Images and QC of blog images | Recurring |  | 8/week
| 4 | Website Images ¦ Banners ¦ UI/UX | Recurring |  | 8/week
| 7 | Certifiacte Campaigns | [5 empty] | Done
| 8 | Refer n Earn ¦ Time to Buy New Campaign |  |  |  | 7th Sept, 2026
| 9 | Price change Banner and creatives
| 10 | New Packaging | One time | Packaging Finalisation |  | 4th Sept, 2026
Realty Canvas | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Social Media Assets | Recurring | Statics ¦ Carousels ¦ Infographics Thumbnails | 2026-05-07
| 4 | Website Images and Banners | As per requirments
TalentiFi-X | S.No. | Deliverables | Type of Deliverable | Formats | Numbers/week | Timeline | Requirements | Status
| 1 | Social Media Calendar Assets(TX and Chet) | Recurring | Statics ¦ Carousels ¦ Infographics Thumbnails | 2026-05-07
| 2 | Blog Images | Recurring |  | 5/week |  |  | In progress
| 3 | Website new pages UI | Recurring |  | 2/week |  | Need content for new pages Manpreet Jangra
Digitally Next | S.No. | Deliverables | Type of Deliverable | Formats | Numbers/week | Timeline | Requirements | Status
| 1 | Social Media Calendar Assets | Recurring | Statics ¦ Carousels ¦ Infographics Thumbnails | 2026-05-07 |  |  | In progress
| 2 | Blog Images | Recurring |  | 5/week |  |  | In progress
| 3 | Website new pages UI | Recurring |  | 2/week
| 4 | Case study pages and Assets |  |  |  | 7th Sept, 2026
Rudione/Leocym | S.No. | Deliverables | Type of Deliverable | Formats | Numbers/week | Timeline | Requirements | Status |  | Major project Timeline: Content: 03 August - 04 August : Homepage 05 August - 06 August : Single Product page / Category Page
| 1 | Packaging (5 excluding Drain ordkill) | One time |  |  | 1st sept, 2026 (Closure with all changes feedback)
| 2 | UI/UX | One time |  |  | 3rd sept, 2026 (According to new content) | Need Webpage Content
| 3 | Wireframe | One time |  |  |  |  | Done
Happy Ganga | S.No. | Deliverables | Type of Deliverable | Formats | Numbers/week | Timeline | Requirements | Status |  | Major project Timeline: Content: 04 - 05 August : Homepage 06 - 07 August : Single Product page / Category Page
| 1 | Packaging (3 product packaging) | One time |  |  | 1st sept, 2026 (Closure with all changes feedback) |  | ON HOLD
| 2 | UI/UX | One time |  |  | 2nd sept, 2026 | Need Webpage Content
| 3 | Social media assets | Recurring |  |  | 7th Sept, 2026

## Video
KYG | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Video on how to collect your sample | One time | Long form and Reel |  |  |  | Done
| 2 | Intro Video: Main Brand Launch Video | One time | Long form and Reel | 2
| 3 | How Genetic Testing Works? | Recurring | Reel | 2/week
|  | Motion video YT videos |  |  |  | 8th Sept
| 4 | Social Media with logo changes in old videos | Recurring | Reels: Short & Long form | 4/week |  |  | In progress
| 6 | Intro video (View reference video) | One time | https://www.instagram.com/reel/DVh9-zvESQT/?igsh=MWZ2bW1oanB2ZDFzYQ== | 1
Hard2Soft | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Meta (Social Media) | Recurring | Reels | 3/week |  |  | In progress
| 2 | YouTube Strategy | Recurring |  | 2/week | 8th Sept |  | In progress
| 3 | Paid Ads | Recurring | Reels | 4/week | 9th Sept
| 4 | Website | One time | Long Form Video | 1 |  |  | Done
| 5 | Critique Video | One time |  | 1 | 8th Sept
Realty Canvas | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Meta (Social Media) | Recurring | Short reels | 3/week
| 2 | YouTube | Recurring | Long Form Video | 1/week
TalentiFi-X | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Chet's videos | Recurring | Reel | 1/week
Digitally Next | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Meta (Social Media) | Recurring | Short reels | 5/week
| 2 | Youtube strategy | Recurring | Long + Short | 2/week | 9th Sept
Rudione | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Meta (Social Media) | Recurring | Short form
| 2 | YouTube | Recurring | Long form+Short form |  | Once approved
Happy Ganga | S.No. | Deliverables | Type of Deliverable | Formats | Numbers | Timeline | Requirements | Status
| 1 | Meta (Social Media) | Recurring | Short form | 3/week
| 2 | YouTube | Recurring | Long form+Short form

## Content
KYG | S.No. | Deliverables | Type of Deliverable | Themes | Formats | Numbers | Timeline | Requirements | Status
| 1 | Website pages | One time |  |  |  | Divide pages, give 3 pages on 10th and rest 2 on 11th August (5:00 PM) | DNA Cardiomet Test, DNA Autoimmune Test, Diabetes PGx, Hypertension, Gastro PharmDx | Done | Mens, Women, Wellness, Skin, Kidney, Eye+2 more total 5 pages Content Copy Completed | BROCHURE
| 2 | Blogs | Recurring |  | Long form | 6/day
| 3 | Performance Ads | Recurring
| 4 | Social Media | Recurring |  |  | 1 month | 7th Sept
| 5 | Content Audit of 13+1 domains | Recurring |  |  |  | 7th Sept
| 6 | Quora and Reddit Calendar | Recurring |  |  | 3-4/week
| 7 | Packaging (Content) | One time
Hard2Soft | S.No. | Deliverables | Type of Deliverable | Themes | Formats | Numbers | Timeline | Requirements | Status |  | BROCURE - b2b
| 1 | Content Audit of website | Recurring |  |  |  | 7th Sept
| 2 | Blogs | Recurring |  | Long form | 5/week
| 3 | Paid Ads scripts (Video) | Recurring | AI generated Ideas | Reels(5) | 3/week | 7th Sept
| 4 | Paid Ads Static (New ideas) |  | Acid cleaning¦ Festival centric¦ Buy protection for your home¦ Pipes¦ Gysers | Static | 5/week | 8th Sept
| 5 | Quora and Reddit Calendar | Recurring |  |  | 3-4/Week
| 6 | Time to Buy amother Unit Campaign (Email marketing) |  |  |  |  | 7th Sept
| 7 | Refer n Earn New Campaign |  |  |  |  | 8th Sept
| 8 | New Packaging content
Realty Canvas | S.No. | Deliverables | Type of Deliverable | Themes | Formats | Numbers | Timeline | Requirements | Status
| 1 | Social Media (Static and Carousel content) | Recurring | Property realty¦ Investment centric¦ Gurgaon centric |  | 1 month calendar | 1st sept, 2026
Rudione/Leocym | S.No. | Deliverables | Type of Deliverable | Themes | Formats | Numbers | Timeline | Requirements | Status
| 1 | Packaging Content | One time |  | As one is almost finalised complete making packaging content for other SKUs too (Odour) |  |  |  | Done |  | brochure - B2B and D2D
| 2 | Website Content | One time |  | Home page+ Product Page+ Category Page |  | homepage(3rd August, 2026), 5th August, 2026 |  | Homepage, About, Contact & Product Page Comleted |  | Major project Timeline: Content: 27 July - 28 July : Homepage 29 July - 30 July : Single Product page 31 July - 3 August : Category / Checkout page 4 August - 5 August : Product listing page 6 August - 7 August : About / Contact page ----- FOR RUDIONE WEBSITE
| 3 | Social Media (Visibility Campaign) | Recurring |  |  |  | Once approved
Happy Ganga | S.No. | Deliverables | Type of Deliverable | Themes | Formats | Numbers | Timeline | Requirements | Status |  | Brochure D2C and B2B
| 1 | Packaging Content | One time |  | As soon as one packaging gets final complete the rest packaging content |  | 2nd sept, 2026
| 2 | Website Content | One time |  | Home page+ Product Page+ Category Page |  | homepage(4th August, 2026), 6th August, 2026 |  | Homepage Content Drafted
| 3 | Social Media | Recurring |  |  | 1 month calendar | 7th Sept